# MIPS Rev 6.0 Firmware

Architecture & Refactoring Plan

SAM3X8E / Arduino Due → STM32H743 migration and modernization

GAA Custom Electronics, LLC   |   Draft v0.1   |   July 2026

# Document Control

| Field | Value |
| --- | --- |
| Document | MIPS Rev 6.0 Firmware Architecture & Refactoring Plan |
| Companion to | MIPS Controller Hardware Upgrade — Design Spec; STM32H743ZIT6 Pin Planning Worksheet |
| Codebase analyzed | github.com/GordonAnderson/MIPS (≈42,700 lines, 41 modules) + github.com/GordonAnderson/GAACE_Core |
| Author / owner | Gordon Anderson, GAA Custom Electronics, LLC |
| Status | Draft — for review |

### Decisions Locked In (from 7/2026 discussion)

| Decision | Choice |
| --- | --- |
| Threading model | Cooperative (ArduinoThread-style), NO preemptive RTOS on the H7 |
| Bus concurrency | PendSV DeferredQueue (I2CQueue/SPIQueue) — ported as-is, promoted to core infrastructure |
| Command processing | GAACE_Core commandProcessor; Serial.cpp decomposed into per-module tables |
| Config storage | GAACE FlashFS + QSPI NOR (replaces DueFlashStorage + SD-for-config) |
| Cleanup scope | Tier 2 — build a clean core first, migrate modules onto it conservatively, clean each as it lands |
| Pulse engine | STM32PulseTimer (TIM2, LL, immediate compare, hazard handling) — already written |
| Middleware mode | HAL USB/QSPI in non-RTOS (polled/interrupt) mode — no RTOS PendSV contention |

# 1. Executive Summary

This plan defines how the MIPS firmware — today ≈42,700 lines across 41 modules on the Arduino Due (SAM3X8E, Cortex-M3, 84 MHz) — migrates to the STM32H743 (Cortex-M7, 480 MHz) while being modernized rather than merely ported. It is the firmware companion to the hardware design specification.

The guiding constraint is that MIPS is deployed and working at 47+ institutions. That fact dominates every decision here: the plan favors preserving a working system at every step, building a clean core foundation first and migrating modules onto it one at a time, so there is always a fallback rather than a big-bang rewrite.

### 1.1 The Central Architectural Decision: No Preemptive RTOS

The most consequential decision is what NOT to change. Despite the initial assumption that an RTOS would be “better,” analysis of the actual code shows the cooperative model is the correct choice for MIPS, for three concrete reasons:

- There is no problem today that cooperative scheduling handles badly — confirmed by the code owner. An RTOS would solve a problem MIPS does not have.

- The hard-real-time requirement (pulse sequencing) is already handled below any RTOS, in hardware timers + ISRs (the pulse engine), which do not need and are not improved by an RTOS.

- The existing DeferredQueue bus-concurrency mechanism is a purpose-built, non-RTOS Cortex-M primitive that uses PendSV. A preemptive RTOS owns PendSV for its own context switching — adopting one would force tearing out and re-solving a concurrency problem that is already solved elegantly. See Section 4.

| ⚡ KEY | Decision: zero preemptive RTOS on the H7. Bare-metal + cooperative scheduler + PendSV DeferredQueue + HAL middleware (USB/QSPI) run in non-RTOS polled/interrupt mode. This is not the conservative-by-default choice — it is the choice the existing architecture actively argues for, and it removes an entire class of concurrency-migration risk. |
| --- | --- |

### 1.2 What “Modernize, Not Port” Means Here (Tier 2)

The migration builds a clean core foundation first — command processor, bus-transaction layer, storage, module registration, the timer subsystem — then brings the 41 modules onto that foundation conservatively, cleaning each as it lands. Concretely, the modernization wins are:

- Decompose the 2,600-line Serial.cpp monolith: each module owns and registers its own command table via GAACE's registerCommands() (this is already on the project TODO list).

- Adopt GAACE_Core's command processor, ring buffer, allocator, Devices, Button, and FlashFS — shared, maintained infrastructure instead of MIPS-private copies.

- Route I2C/SPI access through the DeferredQueue, subsuming many of the 120 hand-placed AtomicBlock critical sections (22 of which directly wrap bus access) into one disciplined mechanism.

- Replace the five SAM3X8-specific libraries (MIPStimer, DueFlashStorage, RTCDue, pwm01, SD-for-config) with H7-native equivalents (STM32PulseTimer, FlashFS+QSPI, H7 RTC, TIM PWM).

- Fix the known bugs already catalogued in the project TODO (ESI board-index copy-paste, RF driver PWM frequency, etc.) as their modules are migrated.

# 2. Current Firmware Architecture (as-is)

Reverse-engineered from the MIPS repository. This is the baseline the plan modernizes.

## 2.1 Execution Model

- Cooperative round-robin scheduler via ArduinoThread (Ivan Seidel). A ThreadController runs due threads to completion in loop(); nothing preempts anything.

- Two system threads today (System @ 10 ms, LED @ 500 ms); each hardware module registers its own thread and menu entries at startup.

- Modules auto-detected at boot by scanning TWI EEPROMs on the module bus (up to 8 boards, board-select addressing).

- Serial command processing runs once per loop() via ProcessSerial(); host comms auto-detect active port (USB native / UART).

- Config saved to SD card (default.cfg) and restored at boot.

## 2.2 Concurrency Primitives

| Primitive | Count / Use | Migration note |
| --- | --- | --- |
| AtomicBlock critical sections | 120 total; 22 directly wrap I2C/SPI/bus access | The 22 bus-related ones are prime candidates to fold into the DeferredQueue; the rest re-audited but mostly ISR-vs-main guards that remain valid under the (unchanged) cooperative model |
| DeferredQueue (I2C acquire/queue) | Existing MIPS mechanism, recently rewritten generic | KEEP — ported as-is, promoted to core infrastructure (Section 4) |
| Pulse-engine ISRs (MIPStimer) | Table.cpp pulse sequence generation | Replaced by STM32PulseTimer (Section 5) |

## 2.3 Module Inventory & Size

41 modules; the largest (migration-effort proxy) are ARB (3,030), DCbias (2,749), Twave (2,623), Serial (2,617), Table (2,499), FAIMS (2,377), Hardware (2,201). Serial.cpp is a cross-cutting monolith holding ~574 command entries for all modules — the #1 decomposition target.

## 2.4 SAM3X8-Specific Dependencies (must be replaced)

| Library | Role today | H7 replacement |
| --- | --- | --- |
| MIPStimer | DueTimer-derived pulse/timer engine (TC compare effects, TIOA) | STM32PulseTimer (TIM2, LL) — already written (Section 5) |
| DueFlashStorage | Emulated EEPROM in Due flash | GAACE FlashFS on QSPI NOR (Section 6) |
| RTCDue / softRTC / Seeed_RTC | Real-time clock | STM32H7 on-chip RTC (LSE 32.768 kHz) |
| pwm01 | Due PWM helper | STM32 TIM PWM (TIM1 bank, per hardware spec §5.4) |
| SD (for config) | default.cfg storage | QSPI FlashFS for config; SD (display module) remains for bulk/docs via MSC |
| Adafruit_ILI9340 / GFX | TFT driver | Retain — SPI-based, portable; re-point to STM32 SPI |

# 3. Target Architecture (to-be)

A layered, bare-metal (no preemptive RTOS) architecture. Lower layers are the clean core built first; modules sit on top and are migrated onto it one at a time.

| Layer | Contents | Source |
| --- | --- | --- |
| Application / UI | Menu, Dialog, Encoder, TFT display | MIPS (refactored) |
| Modules (41) | DCbias, RFdriver, ARB, Twave, FAIMS, ESI, Table, … each owning its command table | MIPS (migrated onto new core) |
| Cooperative scheduler | ArduinoThread-equivalent thread controller | ported / thin re-impl |
| Command processor | GAACE commandProcessor + ringBuffer + charAllocate; per-module CommandLists | GAACE_Core |
| Bus transaction layer | DeferredQueue + I2CQueue + SPIQueue (PendSV-driven) | uploaded, ported as-is |
| Device drivers | GAACE Devices (AD5592R/AD5593R/DAC8571/MCP4725), Button, module-specific chip drivers | GAACE_Core + MIPS |
| Storage | GAACE FlashFS (FatFs) on QSPI NOR for config; SD via HAL for bulk | GAACE_Core + HAL |
| Timer subsystem | STM32PulseTimer (TIM2) + PWM bank (TIM1) + clocks (TIM3/4/5/8) + delay (TIM6/7) | written / per hardware spec §5.4 |
| Middleware (non-RTOS) | USB composite CDC+MSC, QSPI — HAL in polled/interrupt mode | STM32Cube HAL |
| HAL / LL + CMSIS | STM32H743 peripheral access | STM32Cube |

| ℹ INFO | The dividing line: timing-critical and concurrency-critical code (pulse engine, bus queue, scheduler) is bare-metal LL/CMSIS for determinism; stack-heavy convenience code (USB, QSPI/FatFs) is HAL. No layer depends on a preemptive RTOS. This is the hybrid LL/HAL split from the pin-planning worksheet, applied architecturally. |
| --- | --- |

# 4. Bus Transaction Layer (DeferredQueue) — Core Infrastructure

The existing DeferredQueue/I2CQueue/SPIQueue (recently rewritten to be generic) is promoted from a MIPS-internal mechanism to a foundational core layer. It is the single most important reason the no-RTOS decision is correct, and it ports with minimal change.

## 4.1 How It Works (and why it fits bare-metal)

- Fast path: if the bus is idle, the transaction runs immediately in the caller's context — no queuing overhead for the common case.

- ISR-safe deferral: if an ISR needs a busy bus, the transaction (with its own inline data buffer — no dangling stack pointers) is copied into a ring buffer under a short critical section, and PendSV is pended.

- PendSV draining: the Cortex-M PendSV exception runs after real interrupts finish, just before returning to thread mode — so ISR-deferred work drains almost immediately without blocking the ISR.

- Thread-mode self-drain: __get_IPSR() detects thread vs. interrupt context; in thread mode enqueue() drains the backlog itself.

- A single shared PendSV_Handler drains every registered queue instance (all buses, all transaction types) polymorphically via a base-class registry.

| ⚡ KEY | This mechanism USES PendSV as its deferral primitive. A preemptive RTOS also uses PendSV — for its own context switching. The two cannot both own PendSV cleanly. This is the concrete, code-level reason the plan runs bare-metal: keeping this elegant, working primitive is worth more than any benefit a preemptive RTOS would add, and the two are mutually exclusive on PendSV. |
| --- | --- |

## 4.2 Port Effort to H7

Low risk — the queue is already generic Cortex-M, not SAM3X8-specific. It uses noInterrupts()/interrupts(), PendSV, __get_IPSR(), SCB->ICSR, and NVIC priority — all identical on the H7. Port tasks:

- Verify PendSV priority setup against the H7's interrupt-priority-bit count (__NVIC_PRIO_BITS) — the one-time NVIC_SetPriority(PendSV_IRQn, …) call.

- Confirm no HAL component is configured to use PendSV (it will not be, in non-RTOS mode) — this is the coexistence check the whole architecture hinges on.

- Confirm HAL interrupt priorities and the queue's critical-section assumptions coexist (they do; document the priority map).

- Wire the shared PendSV_Handler and the one-time NVIC priority set into system init.

## 4.3 Cleanup Win

Routing module I2C/SPI access through this queue subsumes many of the 22 bus-wrapping AtomicBlock sites (and simplifies others) into one disciplined, testable mechanism — turning scattered ad-hoc critical sections into a single reviewed primitive. This is a concrete Tier-2 modernization, done as each module is migrated.

# 5. Command Processor Migration

MIPS's current Serial.cpp and GAACE_Core's commandProcessor are the same architecture — table-driven, typed, with an identical CommandList linked-list chaining mechanism. GAACE's is the cleaned-up, generalized version. This makes adoption low-risk and directly enables the Serial.cpp decomposition already on the project TODO.

## 5.1 What Maps Directly

| Concept | MIPS today | GAACE | Migration |
| --- | --- | --- | --- |
| Command table | Commands[] array | Command[] array | Near-mechanical |
| Types | CMDstr/int/float/bool/byte/function | same set | Direct |
| Chaining | CommandList linked list | CommandList (identical struct) | Drop-in |
| Get/Set | separate GVER/SNAME entries | ?CMD flags both G/S (table-only, no host impact) | Shrinks tables; host protocol unchanged |
| Range check | hand-rolled in handlers | built into getValue(ll,ul) | Delete hand-rolled validation |
| Multi-stream | ad hoc | registerStream() up to MAX_STREAMS | Cleaner |
| ACK/NAK | 0x06/0x15 | 0x06/0x15 | Identical wire protocol |

## 5.2 What Needs Per-Handler Work

MIPS has specialized handler types GAACE's generic CMDfunction does not: CMDfunctionLine (whole-line, handler tokenizes), CMDlongStr, CMDfun2int1flt, CMDfun2int1str. These back a minority of the ≈574 command entries but need each handler rewritten to GAACE's getValue() style (which is actually cleaner — typed extraction with built-in range checks).

- Simple typed get/set commands (the majority): port mechanically.

- Multi-arg function commands: rewrite each handler to pull tokens via getValue(); delete the positional PCarg1/PCarg2 state-machine dependence.

- CMDfunctionLine bulk/streaming commands (macro & table upload): port carefully or keep in a thin MIPS-specific extension of the processor — do not force into the generic model where subtle line-handling behavior matters.

| ✓ DECIDED | Serial.cpp decomposition and GAACE adoption are the SAME task. Each module gets its own Command[] table + registerCommands() call, moving its commands out of the 2,600-line Serial.cpp monolith into the module that owns them — exactly the refactor already listed on the project TODO. The library provides the clean seam to do the thing already wanted. |
| --- | --- |

# 6. Timer Subsystem & Pulse Engine

Covered in hardware spec §5.4 (allocation) and delivered as the STM32PulseTimer driver. Summary of the firmware-side migration:

| Function | From (SAM3X8) | To (H7) |
| --- | --- | --- |
| Pulse sequence generator | MIPStimer on TC / TIOA compare effects | STM32PulseTimer on TIM2 (LL): immediate mid-period compare, passed-compare hazard handling, ETR trigger, narrow LDAC pulse |
| PWM bank (4ch, 50 kHz, 12-bit) | pwm01 helper | TIM1 (needs ≥204.8 MHz kernel clock for true 12-bit) |
| Burst clocks | — | TIM8 repetition counter |
| Continuous / sub-Hz clocks | ClockGenerator (external CY22393 etc.) + timers | TIM3/TIM4 (continuous), TIM5 (32-bit low-freq) |
| Delay generators | timers | TIM6/TIM7 (basic, interrupt-only) |

| ⚡ KEY | The STM32PulseTimer must be validated against the actual Table.cpp LDAC logic — which has a software-LDAC path (Rev≤1 boards) and a hardware TIOA-toggle path (Rev>1), plus the LDACcapture/LDACctrlLow/LDACctrlHigh/LDACrelease sequence and RampClock->softwareTrigger() coupling. The port preserves the hardware path; confirm the driver's immediate-compare + hazard behavior reproduces the exact pulse timing the Table engine depends on, on a scope, with a real long-period/short-pulse sequence. |
| --- | --- |

# 7. Storage & Configuration

Two distinct storage roles, cleanly separated on the H7:

| Role | Today | Rev 6.0 |
| --- | --- | --- |
| Config / calibration (default.cfg, per-module cal) | DueFlashStorage (emulated EEPROM) + SD | GAACE FlashFS (FatFs) on QSPI NOR — fast, always-present, 1 MB |
| Bulk / docs / thumb-drive | SD card | SD on display module, exposed to host as USB MSC (HAL, non-RTOS) |
| Module EEPROMs (board ID/cal) | TWI EEPROM per module board | Unchanged — same TWI scan, now via I2CQueue |

| ℹ INFO | GAACE FlashFS already has a QSPI transport backend; the port is a new board-config entry for the STM32H743 + W25Q80DV, not a new filesystem. Config-storage code that currently calls DueFlashStorage is rewritten to FatFs file reads/writes — a cleaner, more portable interface than emulated-EEPROM byte offsets. |
| --- | --- |

# 8. Module Migration Strategy

Once the core (Sections 4–7) is in place, the 41 modules migrate onto it one at a time. Ordering is by risk and dependency, not by size alone, so a working system is preserved throughout.

## 8.1 Migration Order Principles

- Core infrastructure first (command processor, DeferredQueue, FlashFS, scheduler, timer subsystem) — nothing else can be validated until this is solid.

- Then a simple, representative module (DCbias — the most-used) to prove the end-to-end path on real hardware: module registration, its command table, bus access via the queue, config via FlashFS.

- Then the rest of the DC/analog family (DCbiasCtrl, DCbiasList, DCBcurrent, DCBswitch, DAC, Analog, ADCdrv) — similar patterns, shared idioms.

- Then RF family (RFdriver, RFamp) — ties to the PWM-frequency TODO bug; validate 12-bit 50 kHz PWM here.

- Then the timing-critical / complex modules LAST (ARB, Twave, FAIMS, FAIMSfb, HOFAIMS, Table, Compressor, ARBcompressor) — these lean hardest on precise timing and the pulse engine, so migrate them only once the timer subsystem is proven.

- Peripheral/interface modules (ESI, Filament, HVPS, DIO, ClockGenerator, FPGA, etc.) interleaved as dependencies allow.

## 8.2 Per-Module Cleanup Checklist (Tier 2, applied as each lands)

- Move the module's serial commands out of Serial.cpp into its own Command[] table + registerCommands().

- Route its I2C/SPI access through I2CQueue/SPIQueue; remove now-redundant bus AtomicBlocks.

- Replace DueFlashStorage config calls with FlashFS.

- Allocate the module's data structure dynamically (per the TODO RAM-saving item) instead of static.

- Remove dead/commented-out code; replace magic calibration constants with named constants.

- Fix any TODO-catalogued bugs in that module (e.g. ESI board-index copy-paste, ESI loop bounds, RF PWM frequency).

## 8.3 Candidates for Deeper (Tier-3) Rework

Most modules get Tier-2 cleanup. A few are flagged by the code owner's own TODO as deeper problems and are candidates for genuine redesign when migrated — chiefly ESI, whose triple state-bookkeeping (esi/esich/esidata hand-synced globals) is the documented root cause of several bugs. These should be rearchitected, not just ported, but only when reached in the order above — not up front.

# 9. Phased Implementation Plan

Sequenced so a working system exists at the end of every phase. Phases 0–4 build and prove the clean core; Phases 5+ migrate modules onto it. This runs partially in parallel with the hardware bring-up phases in the hardware spec (§9).

| Phase | Work | Exit criteria |
| --- | --- | --- |
| 0 — Toolchain & scaffold | STM32CubeMX project (per pin-planning worksheet), hybrid LL/HAL codegen, bare-metal (no RTOS), GAACE_Core as a library dependency. Cooperative scheduler ported. | Blinks + one UART console alive on H7 bring-up board |
| 1 — Command processor core | Adopt GAACE commandProcessor; bring up a minimal system command table (GVER, GNAME, RESET, GCMDS). Prove get/set + ACK/NAK against the host. | Host can talk to the H7 with the real protocol |
| 2 — Bus transaction layer | Port DeferredQueue/I2CQueue/SPIQueue; wire shared PendSV_Handler + NVIC priority. Verify PendSV coexistence (no RTOS, no HAL PendSV use). | I2C module-EEPROM scan works through the queue; scope-verified deferral |
| 3 — Storage core | FlashFS on QSPI (W25Q80DV board config); config save/restore path. USB MSC (SD, HAL) enumerates. | default.cfg reads/writes on QSPI; thumb-drive visible on host |
| 4 — Timer subsystem | STM32PulseTimer (TIM2) + PWM bank (TIM1) + clock/delay timers. Validate immediate-compare + hazard against a real pulse sequence on a scope. | Pulse engine reproduces Table.cpp timing; 12-bit 50 kHz PWM confirmed |
| 5 — First module (DCbias) | Migrate DCbias end-to-end onto the new core: registration, own command table, bus via queue, config via FlashFS. This is the template all other modules follow. | DCbias fully functional on H7; migration pattern proven & documented |
| 6 — DC/analog family | DCbiasCtrl, DCbiasList, DCBcurrent, DCBswitch, DAC, Analog, ADCdrv onto the core, each with per-module cleanup checklist (§8.2). | Family functional; Serial.cpp shrinking as commands move out |
| 7 — RF family | RFdriver, RFamp; fix the RF PWM-frequency TODO bug; validate against the new TIM1 PWM. | RF modules functional; PWM bug closed |
| 8 — Timing-critical family | ARB, Twave, FAIMS, FAIMSfb, HOFAIMS, Table, Compressor, ARBcompressor — the pulse-engine-dependent modules, migrated last. | Full pulse/waveform functionality validated |
| 9 — Remaining modules | ESI (with Tier-3 state-model rework), Filament, HVPS/HVPSinterface, DIO, ClockGenerator, FPGA, FS7140, SC16IS740, DMSDMSMB, ethernet/WiFi, Log. | All 41 modules migrated; Serial.cpp monolith fully decomposed |
| 10 — System validation | Full-system test across a representative module set; regression against Rev 5.4 behavior; field-update rehearsal; documentation. | Sign-off; ready for field deployment |

| ℹ INFO | Phases 0–4 (the clean core) are the high-value, higher-uncertainty work and should not be rushed — every module phase after them is faster because the pattern is fixed. Phase 5 (DCbias) is the linchpin: once one module is cleanly migrated end-to-end, the rest are repetition of a proven template. |
| --- | --- |

# 10. Firmware Migration Risk Register

| Area | Risk | Detail / mitigation |
| --- | --- | --- |
| PendSV coexistence | LOW (given no-RTOS) | The whole architecture hinges on nothing else owning PendSV. No preemptive RTOS + HAL in non-RTOS mode guarantees this. Verify explicitly in Phase 2; document that no future change may introduce a preemptive RTOS without reworking the DeferredQueue. |
| Pulse-engine timing fidelity | MEDIUM | STM32PulseTimer must reproduce Table.cpp's exact LDAC timing (immediate compare + hazard). Scope-verify in Phase 4 before any pulse-dependent module migrates. |
| 12-bit PWM clock tree | MEDIUM | TIM1 needs ≥204.8 MHz kernel clock; a CubeMX clock-tree setting, easy to miss. Locked in Phase 0, validated Phase 4/7. |
| Command handler rewrites | LOW-MEDIUM | The exotic CMDfunctionLine/multi-arg handlers need per-handler rewrites (§5.2). Bounded, mechanical, but numerous across ≈574 entries. |
| Cooperative model preserved | LOW | No change to the scheduling model = no concurrency-migration risk. This is the deliberate benefit of the no-RTOS decision. |
| Library replacements | LOW-MEDIUM | 5 SAM3X8-specific libs replaced; each has a clear H7 equivalent (§2.4). FlashFS and STM32PulseTimer are the substantive ones. |
| Regression vs. 47+ field deployments | MEDIUM (managed by process) | Mitigated structurally: working system preserved every phase; conservative one-module-at-a-time migration; regression testing against Rev 5.4 behavior in Phase 10. |
| ESI Tier-3 rework | MEDIUM | ESI's state model is a documented bug source; reworking (not just porting) it carries redesign risk, isolated to Phase 9. |

# 11. Effort Shape

A firmware effort of this size resists precise hour estimates, but the shape is clear and useful for planning. Ranges assume one experienced engineer familiar with the codebase; the core phases are front-loaded and the module phases are repetitive.

| Block | Phases | Relative effort | Notes |
| --- | --- | --- | --- |
| Clean core | 0–4 | Large, front-loaded | Highest-value, highest-uncertainty. Command processor, DeferredQueue port, FlashFS, timer subsystem. Do not rush. |
| Template module | 5 | Medium | DCbias end-to-end; establishes the pattern. Slower than later modules because the pattern is being invented. |
| Module families | 6–8 | Large but repetitive | ~30 modules following the Phase-5 template. Per-module effort drops steadily as idioms solidify. Timing-critical family (8) is the most demanding. |
| Long tail + rework | 9 | Medium-large | Remaining modules + ESI Tier-3 redesign. |
| Validation | 10 | Medium | System test, regression, field-update rehearsal, docs. |

| ℹ INFO | The single biggest schedule lever is Phase 5: the cleaner and better-documented the DCbias migration template is, the faster all of Phases 6–8 go. Time invested making the first module migration exemplary pays back across ~30 subsequent modules. This estimate covers firmware only and runs partly in parallel with the hardware bring-up (hardware spec §9) once boards are available. |
| --- | --- |

# 12. Immediate Next Steps

Concrete actions that can begin now, before or alongside hardware:

- Finalize the CubeMX project from the pin-planning worksheet (resolve the 6 flagged pin conflicts), generate the hybrid LL/HAL scaffold.

- Port the DeferredQueue/I2CQueue/SPIQueue to the H7 and unit-test the PendSV path on a bring-up board (Nucleo-H743 or the first Rev 6.0 spin) — this de-risks the architectural keystone early.

- Stand up GAACE commandProcessor with a minimal system command table; prove host comms.

- Validate STM32PulseTimer against Table.cpp timing on a scope — the earlier this is confirmed, the safer Phase 8 becomes.

- Draft the DCbias migration as the reference template, documenting the per-module checklist concretely so Phases 6–8 are mechanical.

| ✓ DECIDED | This plan is ready to execute in the phase order above. It preserves a working MIPS at every step, builds the clean GAACE-based core first, keeps the cooperative + DeferredQueue architecture the code already proves is right, and folds the existing TODO cleanup items into the module-migration flow rather than treating them as separate work. |
| --- | --- |